## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
apartment-hunter
La Plateforme |  |  |  |  | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Anthony Saint-Jean, Aurélien Papillon, Ruta Tamosiunaite
Project Start Date: | 2024-03-25 | [5 empty] | mars | [6 empty] | avril | [34 empty] | mai
Scrolling Increment: | 1 | time axis 2024-03-26 to 2024-05-20
Milestone description | Category | Assigned to | Progress | Start | Days | Material | bar: 2024-03-26 to 2024-05-20
Data Processing
Data Summary | On Track | Ruta | 100% | 2024-03-26 | 1 | pd
Deduplication | On Track | Anthony, Ruta | 100% | 2024-03-27 | 1 | pd
Correcting outliers | On Track | Aurelien | 100% | 2024-03-27 | 2 | pd, plt, sns
Finding missing values | On Track | Aurelien | 100% | 2024-03-27 | 1
Data Transformation | On Track | Aurelien | 10% | 2024-03-28 | 1
Exploratory Data Analysis
Univariate Analysis | On Track | Aurelien
Bivariate Analysis | On Track
Multivariate Analysis | On Track
PowerBI Visualization | On Track | Anthony
Data Modelling
Theory of Regression Algorithms | On Track | Ruta | 0% | 2024-03-28 | 1
3 Regression Algorithms & Evaluation | On Track
Models comparison | On Track
Model Fine-tuning | On Track
Flask App Deployment
Flask App | On Track
Docker Environment | On Track
Documentation
ReadMe | On Track
PowerPoint Presentation | On Track
Note on B16: (creating new features, normalizing or scaling variables)

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-03-28 |  |  |  |  | mars | [6 empty] | avril | [27 empty] | mai
Scrolling Increment: | 1 | time axis 2024-03-29 to 2024-05-23
Milestone description | Category | Assigned to | Progress | Start | Days | bar: 2024-03-29 to 2024-05-23
TITLE 1
Task 1 | Goal | Name | 25% | 2024-03-28 | 3 | 2024-03-29: 2; 2024-03-30: 2
Task 2 | Milestone |  |  | 2024-04-02 | 1 | bar: 2024-04-02
Task 3 | Low Risk |  | 50% | 2024-03-25 | 10
Task 4 | Milestone |  |  | 2024-04-17 | 1 | bar: 2024-04-17
Task 5 | Med Risk |  | 10% | 2024-04-03 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-04-03 | 13
Task 2 | On Track |  | 50% | 2024-04-05 | 9
Task 3 | Low Risk |  | 33% | 2024-04-10 | 11
Task 4 | Milestone |  |  | 2024-04-12 | 1 | bar: 2024-04-12
Task 5 |  |  |  | 2024-04-13 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-04-12 | 4
Task 2 | Med Risk |  |  | 2024-04-15 | 14
Task 3 | On Track |  |  | 2024-04-30 | 6
Task 4 | Goal |  |  | 2024-05-04 | 3 | 2024-05-04: 2; 2024-05-05: 2; 2024-05-06: 2
Task 5 | Low Risk |  |  | 2024-04-03 | 19
TITLE 4
Task 1 |  |  |  | 2024-05-07 | 15
Task 2 |  |  |  | 2024-05-21 | 5
Task 3 | Milestone |  |  | 2024-07-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Colour
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-03-28 |  |  |  |  | mars | [6 empty] | avril | [27 empty] | mai
Scrolling Increment: | 0 | time axis 2024-03-28 to 2024-05-22
Milestone description | Category | Assigned to | Progress | Start | Days | bar: 2024-03-28 to 2024-05-22
TITLE 1
Task 1 | Goal | Name | 25% | 2024-03-26 | 3 | 2024-03-28: 2
Task 2 | Milestone |  |  | 2024-04-02 | 1 | bar: 2024-04-02
Task 3 | Low Risk |  | 50% | 2024-03-26 | 10
Task 4 | Milestone |  |  | 2024-04-15 | 1 | bar: 2024-04-15
Task 5 | Med Risk |  | 10% | 2024-04-01 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-04-01 | 13
Task 2 | On Track |  | 50% | 2024-04-03 | 9
Task 3 | Low Risk |  | 33% | 2024-04-08 | 11
Task 4 | Milestone |  |  | 2024-04-10 | 1 | bar: 2024-04-10
Task 5 |  |  |  | 2024-04-11 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-04-10 | 4
Task 2 | Med Risk |  |  | 2024-04-13 | 14
Task 3 | On Track |  |  | 2024-04-28 | 6
Task 4 | Goal |  |  | 2024-05-02 | 3 | 2024-05-02: 2; 2024-05-03: 2; 2024-05-04: 2
Task 5 | Low Risk |  |  | 2024-04-01 | 19
TITLE 4
Task 1 |  |  |  | 2024-05-05 | 15
Task 2 |  |  |  | 2024-05-19 | 5
Task 3 | Milestone |  |  | 2024-06-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one