## Light
apartment-hunter
La Plateforme
Anthony Saint-Jean, Aurélien Papillon, Ruta Tamosiunaite
Project Start Date: |  | 2024-03-25 |  |  |  |  | mars | [6 empty] | avril
Scrolling Increment: | 0 | [5 empty] | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20
Milestone description | Category | Assigned to | Progress | Start | Days | Material | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20
Data Processing
Data Summary | On Track | Ruta | 100% | 2024-03-26 | 1 | pd
Deduplication | On Track | Anthony, Ruta | 100% | 2024-03-27 | 1 | pd
Correcting outliers | On Track | Aurélien | 100% | 2024-03-27 | 1 | pd, plt, sns
Finding missing values | On Track | Aurélien | 100% | 2024-03-27 | 1
Data Transformation | On Track | Aurélien | 100% | 2024-03-28 | 2
Exploratory Data Analysis
Univariate Analysis | On Track | Aurélien | 100% | 2024-03-28 | 1
Bivariate Analysis | On Track | Aurélien | 100% | 2024-03-28 | 1
Multivariate Analysis | On Track | Aurélien | 100% | 2024-03-28 | 1
PowerBI Visualization | On Track | Anthony | 5% | 2024-03-29 | 1 | PowerBI
Data Modelling
Regression Algorithms Overview | On Track | Ruta | 0% | 2024-03-28 | 1
Regression Algorithms & Evaluation | On Track | Aurélien, Anthony, Ruta
Models comparison | On Track | Aurélien, Anthony, Ruta
Model Fine-tuning | On Track | Aurélien, Anthony, Ruta
Flask App Deployment
Flask App | On Track | Ruta
Docker Environment | On Track
Documentation
ReadMe | On Track
PowerPoint Presentation | On Track | Aurélien, Anthony, Ruta
Note on B16: (creating new features, normalizing or scaling variables)