## Light
apartment-hunter
La Plateforme
Anthony Saint-Jean, Aurélien Papillon, Ruta Tamosiunaite
Project Start Date: |  | 2024-03-25 |  |  |  |  | mars | [6 empty] | avril
Scrolling Increment: | 0 | [5 empty] | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20
Milestone description | Category | Assigned to | Progress | Start | Days | Material | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20
Data Processing
Data Summary | On Track | Ruta | 100% | 2024-03-26 | 1 | pd
Deduplication | On Track | Anthony, Ruta | 100% | 2024-03-27 | 1 | pd
Data Transformation | On Track | Aurélien, Ruta | 100% | 2024-03-27 | 2 | pd, np
Correcting outliers | On Track | Aurélien | 100% | 2024-03-27 | 1 | pd, plt, sns
Finding missing values | On Track | Aurélien | 100% | 2024-03-27 | 1 | plt, sns
Exploratory Data Analysis
Univariate Analysis | On Track | Aurélien | 100% | 2024-03-29 | 1 | plt, sns
Correlation & Association Tests | On Track | Aurélien | 100% | 2024-03-29 | 1 | np, plt
Multivariate Analysis | On Track | Ruta | 100% | 2024-03-30 | 1 | np, plt
PowerBI Visualization | On Track | Anthony | 5% | 2024-04-15 | 3 | PowerBI
Data Modelling
Regression Algorithms Overview | On Track | Ruta | 0% | 2024-04-15 | 1 | px
Regression Algorithms Training & Evaluation | On Track | Aurélien, Anthony, Ruta |  | 2024-04-15 | 3
Models comparison (Grid Search) | On Track | Aurélien, Anthony, Ruta |  | 2024-04-17 | 1 | sklearn
Model Fine-tuning | On Track | Aurélien, Anthony, Ruta |  | 2024-04-17 | 1
Flask App Deployment
Flask App | On Track | Aurélien, Anthony, Ruta |  | 2024-04-18 | 2 | Flask
Docker Environment | On Track | Aurélien, Anthony, Ruta |  | 2024-04-18 | 2 | Docker
Documentation
ReadMe | On Track | Aurélien, Anthony, Ruta |  | 2024-04-19 | 1 | GitHub
PowerPoint Presentation | On Track | Aurélien, Anthony, Ruta |  | 2024-04-19 | 1 | PowerPoint
pd : pandas np : numpy plt : matplotlib.pyplot sns : seaborn px : plotly.express

## Copy for printing
apartment-hunter
La Plateforme
Anthony Saint-Jean, Aurélien Papillon, Ruta Tamosiunaite
Project Start Date: |  | 2024-03-25
[7 empty] | mars |  |  |  |  | avril |  |  |  |  | mai
Milestone description | Category | Assigned to | Progress | Start | Days | Material | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-05-06 | 2024-05-07
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Data Processing
Data Summary | On Track | Ruta | 100% | 2024-03-26 | 1 | pd
Deduplication | On Track | Anthony, Ruta | 100% | 2024-03-27 | 1 | pd
Data Transformation | On Track | Aurélien, Ruta | 100% | 2024-03-27 | 2 | pd, np
Correcting outliers | On Track | Aurélien | 100% | 2024-03-27 | 1 | pd, plt, sns
Finding missing values | On Track | Aurélien | 100% | 2024-03-27 | 1 | plt, sns
Exploratory Data Analysis
Univariate Analysis | On Track | Aurélien | 100% | 2024-03-29 | 1 | plt, sns
Correlation & Association Tests | On Track | Aurélien | 100% | 2024-03-29 | 1 | np, plt
Multivariate Analysis | On Track | Ruta | 100% | 2024-04-15 | 1 | np, plt, px
PowerBI Visualization | On Track | Anthony | 5% | 2024-04-15 | 2 | PowerBI
Data Modelling
Regression Algorithms Overview | On Track | Ruta | 0% | 2024-04-15 | 2 | -
Regression Algorithms Training & Evaluation | On Track | Aurélien |  | 2024-04-16 | 3 | sklearn
Models comparison (Grid Search) | On Track | Aurélien |  | 2024-04-17 | 2 | sklearn
Flask App Deployment
Flask App | On Track | Anthony |  | 2024-04-18 | 2 | Flask, joblib
Docker Environment | On Track | Anthony |  | 2024-05-06 | 1 | Docker
Documentation
ReadMe | On Track | Ruta |  | 2024-05-06 | 1 | GitHub
PowerPoint Presentation | On Track | Aurélien, Anthony, Ruta |  | 2024-05-06 | 1 | PowerPoint
pd : pandas np : numpy plt : matplotlib.pyplot sns : seaborn px : plotly.express